## Sheet1
Austins Timeline and Effort Matrix
Milestone | Task Type | Task Description | Start Date | End Date | Estimated Hours
1. Determine scope and design of project | Planning/Design | Map out what Arcadio will consists of. Create mock ups of the physical cabinet and web interface. Determine what features the device will have. | Aug 10th 2020 | October 15th 2020 | 10
2. Research and acquire parts needed for prototype | Planning/Design | Purchase the needed parts after researching requirements needed for 2D gaming and web hosting. Minimum of Computer/Web Server and device to send input from arcade components. (Later decided on Raspberry Pi 4 8GB and Arduino Mega duo) | October 15th 2020 | February 1st 2021 | 2
3. Setup Raspberry Pi 4 as web server (LAMP) | Development | Set up server on Raspberry Pi 4 with a Linux OS, with APACE, MySQL, and PHP for additional dynamic content on web. | November 15th 2020 | December 1st 2020 | 2
4. Create working prototype of webpage | Development | Program and develop a web page that will allow users to upload their games to the Raspberry Pi 4, restarting and launching game after hitting confirm. | December 1st 2020 | February 1st 2021 | 4
5. Purchase sensors/arcade components | Development | Purchase the components/parts needed to create a working prototype of the projects internals. | January 15th 2021 | February 1st 2021 | 2
6. Create working prototype of sensor input | Development | Design and create a working prototype of the sensor input on a cardboard box before moving into future Arcadio frame | January 15th 2021 | February 1st 2021 | 10
7. Program sensor input to games via webpage | Development | Program sensor input controls in webpage to allow users to make adjustments | Febrary 1st 2021 | February 15th 2021 | 10
8. Purchase materials for Arcadio frame | Development | Purchase all wood/acrylic needed to construct the frame. | Febrary 1st 2021 | February 15th 2021 | 2
9. Construct Arcadio frame | Construction | Build the frame using the acquired materials. | Febrary 1st 2021 | March 1st 2021 | 5
10. Attach components inside of Arcadio, wire up | Construction | Install all internals to Arcadio cabinet. Ensure all wiring remains consistent from prototype, and manage wires properly. | Febrary 1st 2021 | March 1st 2021 | 6
11. Test Arcadio and make fixes | Testing | Test with several games of varying control styles, note any bugs and work on fixing them. Polish project before having another user test. Update all documentation for project with photos, scripts, and code running behind the webpage. | March 1st 2021 | March 15th 2021 | 10
12. Have someone test Arcadio | Testing | Have a user test Arcadio by uploading a game to the device via the web interface. Have the user test the coin operator to play and write down all feedback. | March 15th 2021 | March 30th 2021 | 1
13. Make finishing touches | Development | Based on feedback work on fixing bugs seen in Arcadio. Add/Remove features as determined by test and polish project to a final state. | April 1st 2021 | April 11th 2021 | 5

## Sheet2
Task Name | Start | End | Duration (days)
1. Determine scope and design of project | 2020-08-10 | 2020-10-15 | 66
2. Research and acquire parts needed for prototype | 2020-10-15 | 2021-02-01 | 109
3. Setup Raspberry Pi 4 as web server (LAMP) | 2020-11-15 | 2020-12-01 | 16
4. Create working prototype of webpage | 2020-12-01 | 2021-02-01 | 62
5. Purchase sensors/arcade components | 2021-01-15 | 2021-02-01 | 17
6. Create working prototype of sensor input | 2021-01-15 | 2021-02-01 | 17
7. Program sensor input to games via webpage | 2021-02-01 | 2021-02-15 | 14
8. Purchase materials for Arcadio frame | 2021-02-01 | 2021-02-15 | 14
9. Construct Arcadio frame | 2021-02-01 | 2021-03-01 | 28
10. Attach components inside of Arcadio, wire up | 2021-02-01 | 2021-03-01 | 28
11. Test Arcadio and make fixes | 2021-03-01 | 2021-03-15 | 14
12. Have someone test Arcadio | 2021-03-15 | 2021-03-30 | 15
13. Make finishing touches | 2021-04-01 | 2021-04-11 | 10